## Slide 1: Project last part planning
Edouard Audit – Project coordinator
2018.04.12th, EoCoE Face-to-Face Meeting, Bath (UK)

## Slide 2: Next EoCoE and HPC events
EoCoE events:
  Performance Engineering Hackathon – Maison de la Simulation - Paris, Saclay (France) – 11th-13th June 2018
  European Materials Research Society – Strasbourg (France) – 18th June 2018
  EoCoE Last Face-to-Face meeting
  => 17th-18th-19th September 2018 (Cyprus) – SAVE THE DATE!
HPC events:
  EASC 2018 – Edinburgh (Scotland) – 17th-19th April 2018
  HPC summit 2018 – Ljubljana (Slovenia) – 28th May – 1st June2018
    EoCoE representation => Paul Gibbon’s talk.
  ISC 2018 – Frankfurt (Germany) – 24th-28th June

## Slide 3: Late Deliverables
All the deliverables must be uploaded before end September 2018:
  D2.6 Formulation for optimization under uncertainty (30th September 2017)
  D6.14 Report on knowledge transfer for co-design of Exascale architectures (30th September 2017)
  D1.3 Application support outcome (report) (30th January 2018)
  D1.5 Application support outcome (code) (30th January 2018)
  D1.7 Software technology improvement (report) (30th January 2018)
  D1.9 Software technology improvement (code) (30th January 2018)
  D1.11 Applied research activities outcome (report) (30th January 2018)
  D1.13 Applied research activities outcome (code) (30th January 2018)
  D2.7 Demonstrator of an ultralarge meteorological forecast ensemble system (31st March 2018)

## Slide 4: Next Deliverables
WP1 => 6 deliverables
WP2 => 4 deliverables
WP3 => 1 deliverables
WP1 | D1.4 | D21 | D1.4.1 Application support outcome (report)
WP1 | D1.6 | D23 | D1.4.2 Application support outcome (code)
WP1 | D1.8 | D25 | D1.6.1 – Software technology improvement (report)
WP1 | D1.10 | D27 | D1.6.2 – Software technology improvement (code)
WP1 | D1.12 | D29 | D1.8.1 – Applied research activities outcome (report)
WP1 | D1.14 | D31 | D1.8.2 – Applied research activities outcome (code)
WP2 | D2.10 | D60 | D2.10 GHI forecasts at local scale
WP2 | D2.11 | D61 | D2.11 Statistical calibration of ensemble
WP2 | D2.8 | D58 | D2.8 Paper on statistical calibration
WP2 | D2.9 | D59 | D2.9 Paper on GHI forecasting
WP3 | D3.4 | D65 | D3.4 Application lines: benchmark and results

## Slide 5: Next Deliverables
WP4 => 4 deliverables
WP5 => 4 deliverables
WP4 | D4.3 | D38 | D4.3 Specific layout of energy supply system for city quarter based on geothermal energy alone or in combination with heat and power (CHP) plant
WP4 | D4.4 | D39 | D4.4 Estimates of hydrologic variables relevant to hydropower (e.g. stream discharge, water storages) including uncertainty estimates
WP4 | D4.5 | D40 | D4.5 Estimates of hydraulic variables and uncertainty estimates for major rivers in France used for hydropower production
WP4 | D4.6 | D41 | D4.6 Report on hydropower potential scenarios analysis
WP5 | D5.2 | D67 | D5.2– Flux-surface Meshing Software
WP5 | D5.3 | D68 | D5.3 – Optimized coupling of Monte-Carlo and fluid transport code
WP5 | D5.4 | D69 | D5.4 – Towards the coupling of gyrokinetic and fluid codes
WP5 | D5.5 | D70 | D5.5 – Towards ITER relevant simulations

## Slide 6: Next Deliverables
WP6 => 5 deliverables
WP7 => 3 deliverables
WP6 | D6.15 | D15 | D 6.15 Final conference report
WP6 | D6.16 | D16 | D 6.16 Delivery of one long movie on EoCoE overall results
WP6 | D6.17 | D17 | D 6.17 Assessment report and exploitation plan– including patents/spinoffs
WP6 | D6.5 | D5 | D6.5 Third annual workshop report
WP6 | D6.8 | D8 | D 6.8 Third annual dissemination report
WP7 | D7.4 | D45 | Long-term impact assessment
WP7 | D7.7 | D48 | Risk Analysis Contingency Plan - M36
36 deliverables until the end of the project

## Slide 7: Dissemination
Newsletters => 1 more
Videos
  General presentation of the project will be soon available
  Long EoCoE movie presentation
  EoCoE Youtube channel => Subscribe!
  Webinars
  Large public conference (Last F2F meeting - Cyprus)

## Slide 8: Impacts
Impact 1: Improved access to computing applications and expertise that enables researchers and industry to be more productive, leading to scientific excellence.
  Number of computing hours saved on the PRACE infrastructure each year: > 50 Mh/y (by the end of the project).
  Number of applications using EoCoE supported numerical libraries and tools: increase > 50%
  Proportion of EoCoE application teams that benefit from HPC expertise: 100%
  Number of teams outside EoCoE that benefit from HPC expertise: > 20
Impact 2: Improved competitiveness for companies and SMEs through access to CoE expertise and services.
  Number of consortia / industries / SMEs supported: >10 (consultancy, application optimization, usage of EoCoE supported libraries)

## Slide 9: Impacts
Impact 3: European leadership in applications that address societal challenges or are important for industrial applications through better code performance and better code maintenance and availability.
  A minimum of ten (10) codes, will be improved (from 10%, for more mature codes, up to several factors for the codes which have not yet been (re)designed for many-core computers).
  Number of publications using EoCoE supported applications or libraries: >50/year by the end of the project.
  Number of cutting-edge scientific codes modules, HPC tools, improved numerical methods stored, maintained and disseminated through the open library

## Slide 10: Impacts
Impact 4: More scientists and engineers trained in the use of computational methods and optimization of applications. On the one hand, close collaboration with PRACE will ease dissemination of knowledge through training modules proposed to the PRACE Advanced Training Centres (PATCs). Collaborations with Pan-European structures dedicated to industrial/academic consortia funding will be another vector to disseminate skills and knowledge.
  Number of conferences where EoCoE HPC simulation message is delivered specifically to SMEs and industry: > 10
  Number of HPC courses modules created or updated with new EoCoE expertise (ex: FTI, I/Os): 5
  Number of PATCs’ sessions using EoCoE training materials: 20
  Number of attendees to training sessions with EoCoE training materials: 150 persons
  Number of course session dedicated to PMEs: 2
  Number of hired personnel mentored by EoCoE experts: >20

## Slide 11: EoCoE Last part timeline
EoCoE II Proposal
Dec. 17
Jan. 18
Feb. 18
Mar. 18
Apr. 18
May 18
June 18
July 18
Aug.18
Sept. 18
EC Check
2018.03.22
F2F CLOSING MEETING
IN CYPRUS
EoCoE II Proposal written
EoCoE II Proposal review
F2F MEETING IN BATH
EoCoE II SC/TC
EoCoE II EC validation
EoCoE II start
ISC
Frankfurt
24-28 June
EASC
Edinburgh
17-19 April
HPC S.
Ljubljana
28 May – 1 June
PE WS
Paris (Saclay)
11-14 Dec.
EERA WS
Naples
15 Dec.
HPCS DLS
2017.12.18
EASCDL
2017.12.11
ISC DL
2018.02.28
Oct. 18
Hackathon
11-13 June
EMRS
18 June

## Slide 12: Reminders
Impacts => send them to Nathalie Girard
OpenAire process on the ECP
All the EoCoE events and news are on the website
Dissemination table on the ECP
Publications EoCoE acknowledgement:
"This work was supported by the Energy oriented Centre of Excellence (EoCoE), grant agreement number 676629, funded within the Horizon2020 framework of the European Union."

## Slide 13: SAVE THE DATE! EoCoE Last Face-to-Face meeting 17th-18th-19th September 2018 (Cyprus)
Thank you!